CAIS No. 308 November 2025

Administration and Inspection Activities for

Tack Coating and Joint Painting

(As Specified in OPSS 308)

308.01	SCOPE

This CAIS covers the construction administration and inspection requirements for tack coating and joint painting as specified in OPSS 308, November 2025.

308.02	REFERENCES

This CAIS refers to the following standards, specifications, or publications:

Ontario Provincial Standard Specifications, Construction

OPSS 308	Tack Coating and Joint Painting

Construction Administration and Inspection Specifications (CAIS):

CAIS 1103	Emulsified Asphalt

MTO Forms:

PH-CC-135	Determining the Payment Adjustment for Tack Coat

PH-CC-139	Bituminous Mix and Core Sample Identification

PH-CC-325	Method B: Field Verification of Tack Coat Application Rate

PH-CC-326	Method C: Field Verification of Tack Coat Application Rate by Tack Coat Distributor’s Display

PH-CC-349	Bituminous Material Product Sample Form

MTO Guidelines:

Field Guide for the Acceptance of Hot Mix Asphalt and Hot-applied Rubberized Asphalt Waterproofing Membrane

ASTM International:

ASTM D5/D5M	Standard Test Method for Penetration of Bituminous Materials

ASTM D2995	Standard Practice for Estimating Application Rate and Residual Application Rate of Bituminous Distributors

ASTM D3665	Standard Practice for Random Sampling of Construction Materials

ASTM D6997	Standard Test Method for Distillation of Emulsified Asphalt

American Association of State Highway and Transportation Officials Standards:

AASHTO R66	Standard Practice for Sampling Asphalt Materials

AASHTO T407	Standard Method of Test for Determining the Interlayer Shear Strength (ISS) of Asphalt Pavement Layers

308.03	DEFINITIONS

For the purpose of this CAIS, the definitions shall be as specified in OPSS 308.

308.04	DESIGN AND SUBMISSION REQUIREMENTS

308.04.01	Submission Requirements

Administrative Activities:

| 1 | M | Receive and Review documentation identifying the proposed tack coat supplier and applicator of the product, tack coat type, typical test results, minimum residue, minimum application rate, safety data sheets, and any other information for the safe handling and storage of the tack coat product in the timeline specified. | - |
| --- | --- | --- | --- |
| 2 | - | Receive and Review the proposals for the use of any alternative tack coat and joint painting material (proposal) in the timelines specified. | - |
| 3 | - | Check that the proposal includes the components specified in OPSS 308. |  |
| 4 | - | Discuss the proposal with the Regional Quality Assurance Section as outlined in the Field Guide for the Acceptance of Hot Mix Asphalt and Bridge Deck Waterproofing. Reply to the Contractor within 5 Business Days of receiving the request. | - |
| 5 | - | Notify the Contractor, within 5 Business Days of receiving the request, of the status of the review. | - |

308.05	MATERIALS

Administrative Activities:

| 1 | M | Check that tack coat and joint painting material consists of SS-1 or SS-1H or SS-1HH emulsified asphalt diluted up to a maximum of 50% with water (maximum dilution 1:1). Diluted tack coat materials requirements shall be administered according to OPSS 308Table 1. | - |
| --- | --- | --- | --- |
| 2 | - | Undiluted material requirements shall be administered according to CAIS 1103. | - |

308.06	EQUIPMENT

308.06.01	Joint Painting Distributors

Administrative Activities:

| 1 | M | Check that joint painting distributors are as specified in OPSS 308. | - |
| --- | --- | --- | --- |

308.06.02	Tack Coat Distributors

Inspection Activities:

| 1 | M | Check that the tack coat distributors are as specified in OPSS 308. | 100% |
| --- | --- | --- | --- |

Administrative Activities:

| 1 | M | Receive and Review the calibration documentation for the tack coat distribution system from the Contractor. | - |
| --- | --- | --- | --- |
| 2 | M | Check that the tack coat distribution system was calibrated in the last 12 months by the manufacturer, or its authorized representative. | - |

308.07	CONSTRUCTION

308.07.01	Operational Constraints

Inspection Activities:

| 1 | M | Check that surfaces to be tack coated and joint painted are free of all water and contamination, such as dirt, mud, loose aggregate, or debris. | 100% |
| --- | --- | --- | --- |
| 2 | - | Check that tack coat is placed sufficiently ahead of the paving operation to allow for curing as specified in OPSS 308. | 100% |
| 3 | - | Check that paving and construction equipment are not permitted on the tack coat until the tack coat has broken and set. Check that there is no bare material due to tracking by construction equipment or vehicles. | 100% |
| 4 | M | Check that protection board is dry and clean when tack coat is applied. | 100% |
| 5 | M | Check that hot mix asphalt (HMA) is not placed on the tack-coated areas until the tack coat has properly set. | 100% |
| 6 | - | Check that traffic is prevented from travelling upon the tack coated areas. | 100% |

308.07.02	Tack Coat Application

Inspection Activities:

| 1 | M | Check that tack coat is applied to the surfaces specified in OPSS 308. | 100% |
| --- | --- | --- | --- |

308.07.03	Tack Coat Application Rates

Inspection Activities:

| 1 | M | Verify that tack coat is applied to the surfaces at the application rates as specified in Table 2 of OPSS 308 or an approved proposal submitted by the Contractor. Tack coat application rate shall be verified using LS-325 testing method by the Contract Administrator. | 100% |
| --- | --- | --- | --- |
| 2 | - | Check that the tack coat application is visually uniform. | 100% |

308.07.04	Joint Painting

Inspection Activities:

| 1 | - | Check that joint faces are painted with a thin, uniform, and continuous coating of joint painting material as specified in OPSS 308. | 100% |
| --- | --- | --- | --- |

308.07.05	Material Sampling and Testing

308.07.05.02	Tack Coat

Inspection Activities:

| 1 | M | Witness the tack coat samples being taken at the paving site as specified and in accordance with AASHTO R66. | 100% |
| --- | --- | --- | --- |
| 2 | M | Check that sampling frequency, quantity, and labelling is as specified in OPSS 308 and the Contract Documents. | 100% |
| 3 | M | Complete PH-CC-349 and include it in the sample bag with the corresponding tack coat sample. | 100% |
| 4 | M | Maintain continuous possession of the samples until they are sealed and arrange for the delivery of samples to the Owner’s designated laboratory. | 100% |

308.07.05.03	Pavement Core Samples for Interlayer Shear Strength Testing

Administrative Activities:

| 1 | M | Upon the completion of each lot, Notify the Contractor of each random core sample location. Core shall be obtained no later than the next Business Day after completion of paving as specified in OPSS 308. | - |
| --- | --- | --- | --- |

Inspection Activities:

| 1 | M | Witness core samples for Interlayer Shear Strength testing being taken. Check that core samples are taken as specified in OPSS 308. Check that the core is 150 mm in diameter (145 to 150 mm diameter). | 100% |
| --- | --- | --- | --- |
| 2 | M | Check that sampling frequency, quantity, and labelling is as specified in OPSS 308and the Contract Documents. Check that core samples are marked with traffic direction, lot/sublot number and label includes design lift thickness. | 100% |
| 3 | M | Complete PH-CC-139 form and include in the sample bag with the corresponding core sample. Also, include PH-CC-325 or PH-CC-326 (verification of field application rate) to the core sample. | 100% |
| 4 | M | Maintain continuous possession of the samples until they are sealed and delivered to the Owner’s designated laboratory. | 100% |

308.07.06	Management of Excess Material

Administrative Activities:

| 1 | - | Check that management of excess material is as specified in the Contract Documents. | - |
| --- | --- | --- | --- |

308.08	QUALITY ASSURANCE

308.08.02	Acceptance of Tack Coat Material

308.08.02.01	General

Administrative Activities:

| 1 | M | Receive and Review laboratory and field test results. | - |
| --- | --- | --- | --- |
| 2 | M | Provide test results of each sublot to the Contractor as they become available. | - |

308.08.02.02	Lot and Sublot Sizes

Administrative Activities:

| 1 | M | Prior to HMA placement and after discussion with the Contractor, Determine the size and location of tack coat lots and sublots, as specified in OPSS 308. Verify that there is a separate lot for each specified tack coat application rate used on the Contract. | - |
| --- | --- | --- | --- |
| 2 | - | Terminate sublots when the placement of HMA ceases for a period of 20 Business Days or more. | - |
| 3 | M | Arrange for the delivery of samples to the Owner’s designated laboratory. | - |

308.08.02.03	Basis of Acceptance

308.08.02.03.01	General

Administrative Activities:

| 1 | M | Check that the percent residue of the diluted tack material meets the Table 1 requirements of OPSS 308. | - |
| --- | --- | --- | --- |
| 2 | M | The percent Oil portion of distillate and penetration shall be reported for each sublot for information purposes. | - |

308.08.02.03.02	Weighted Lot Mean for the Percent Residue

Administrative Activities:

| 1 | M | Notify the Contractor of rejected sublots and whether the sublot is subject to repair or pay adjustment. | - |
| --- | --- | --- | --- |
| 2 | M | Complete PH-CC-135 form for determining the payment adjustment for each tack coat lot using weighted lot mean for percent residue as specified in OPSS 308. Notify the Contractor of lot payment factor. | - |

308.08.02.03.04	Referee Testing

Administrative Activities:

| 1 | M | If referee testing for a sublot is invoked by the Contractor, check that the request is within the timeline specified in OPSS 308. Coordinate the referee testing according to the Field Guide for Acceptance of Hot Mix Asphalt and Bridge Deck Waterproofing. | - |
| --- | --- | --- | --- |
| 2 | M | Receive and Review all referee laboratory test results. Provide copies of the test results to the Contractor. | - |
| 3 | M | If a referee percent residue sublot test result is less than 27.5%, then the Contractor shall be charged for the cost of the referee testing of that sublot at the rates specified in the Contract Documents. | - |

308.08.03	Acceptance of Field Application

308.08.03.01	General

Inspection Activities:

| 1 | M | Check visually that the tack coat coverage is uniform and not defective. | 100% |
| --- | --- | --- | --- |
| 2 | M | Visually defective material and non-uniform coverage shall be rejected or repaired as specified in OPSS 308. Notify the Contractor of rejected work and require that the non-uniform coverage area is resprayed prior to paving. | 100% |

308.08.03.02	Verification of Field Tack Coat Application Rate

Inspection Activities:

| 1 | M | Verify the tack coat field application rate according to LS-325 at the start of application of tack coating the first sublot and then every sublot as specified in OPSS 308. | 100% |
| --- | --- | --- | --- |
| 2 | M | Fill in on site PH-CC-325 or PH-CC-326 or any other reporting form as applicable for verification of the tack coat field application rate and include to ISS core sample and also submit to CMS System. | 100% |

Administrative Activities:

| 1 | M | If tack coat field application rate for a sublot does not meet the contract requirements according to OPSS 308, then that sublot is rejectable. Discuss payment adjustment with the MTO Regional Quality Assurance Section. | - |
| --- | --- | --- | --- |

308.08.03.03	Joint Painting Application Rate Acceptance

Inspection Activities:

| 1 | M | Verify that the joint paint application provides a thin, uniform and continuous coating to all joint faces. | 100% |
| --- | --- | --- | --- |

308.08.03.04	Appearance Acceptance

Inspection Activities:

| 1 | M | Check that the tack coat and joint paint application is visually uniform and fully covering the areas specified in the Contract Documents. Areas of insufficient or non-uniform tack coat coverage shall be re-sprayed prior to paving. | 100% |
| --- | --- | --- | --- |

308.08.04	Disposition of HMA Produced with Rejectable Tack Coat

Administrative Activities:

| 1 | M | Determine the dispositions of sublots as specified in OPSS 308. | - |
| --- | --- | --- | --- |

308.09	MEASUREMENT FOR PAYMENT

Administrative Activities:

| 1 | M | Measurement for payment shall be as specified in OPSS 308. | - |
| --- | --- | --- | --- |

308.10	BASIS OF PAYMENT

308.10.01	Tack Coat - Item

Administrative Activities:

| 1 | M | Basis of payment shall be as specified in OPSS 308. | - |
| --- | --- | --- | --- |

308.10.01.02	Payment Adjustment for Tack Coat

Administrative Activities:

| 1 | M | Determine payment adjustment as specified in OPSS 308. | - |
| --- | --- | --- | --- |

WARRANT:	Always with OPSS 313, Construction Specification for Tacking Coating and Joint Painting.